## Slide 1: Public Health Emergency Preparedness (PHEP) and Cities Readiness Initiatives (CRI)
        Pat Bedell
        Project Specialist

## Slide 2: Timelines/Checklist
Grant Year July 1 – June 30
New Grant Year
Work Plans
Invoicing
Annual Reports
End of Year
Description | Complete/Submit By Date*
Budgets and Work Plans for upcoming contract year | Requested in January, due back within 2 weeks
Previous contract year End of Year Work Plans | June 30
Previous contract year final PHEP/CRI invoices | July 15
End of year reports (Inventory List, Tangible Personal Property Report) | June 30
Monthly invoice and invoice tool | 15th of following month

## Slide 3: Four Step Process
Submitting the Budget
Review your last approved budget
Objectives
Work Plan activities
Submitting Invoices
Review calculations
Check supporting documentation
No negative balances on the invoicing tool
Due by the 15th day of the following month
Changing Budgets
Budgets are part of the contract.
Always reach out for assistance
Amendments?
Submitting Reports
Work Plans
Inventory List
Tangible Personal Property Report
End of year reports – due June 30
Contact Annette Lopes at Preparedness@health.mo.gov

## Slide 4: Budget
Travel and Supplies
Supply (consumables) – general office supplies, paper, pens, toner cartridges
Travel costs (hotel, mileage, meals) – only staff paid from preparedness funds.
Other - printing, postage, cell phone services, telephone services, generator maintenance, internet services, conference registration fees, etc.
Equipment
Equipment – Communication equipment, computers, printers
Point of Dispensing (POD) equipment, software, etc.
MOSWIN radios
Generators
Always requires prior approval per CDC.
Already in your approved budget = prior approval
Disposal of equipment – ask for assistance

## Slide 5: Budget Changes
Indirect Cost Rate Changes
New federally negotiated indirect rate agreement?
Send to Preparedness@health.mo.gov.
Other indirect rate changes:
  • only at the beginning of a contract, and
  • prior to any invoice payments.
The new rate cannot exceed 15% modified total direct costs.
Contract amendment required
Budget Reallocations
Less than 10% (excluding indirect) of the original budget = no required prior approval.
Reallocation form required.
Greater than 10% (cumulative) of the original budget = required prior approval
Reallocation form required.
Most likely requires a contract amendment
Reallocating to new budget lines –
contract amendment required
Contact Annette as soon as possible to discuss changes.

## Slide 6: Submitting Invoices
DA-38 and Invoicing Tool
Submit signed itemized DA-38 along with the Excel invoice tool as separate attachments to: Preparedness@health.mo.gov
Invoice tools ≠ negative balances
Negative balances require a reallocation and potentially a contract amendment.
Backup documentation is not required with the invoice. You will be notified if an invoice is selected as part of monitoring activities.

## Slide 7: Submitting Reports
Tangible Personal Property Report
What to report:
Federally owned or purchased using grant funds?
• Description
• Identification (Serial number, model number, etc.)
• Acquisition date
• Condition
Form SF-428S
Inventory List
Report all supplies and equipment purchased with preparedness funds in the current budget year.
An attached printout from your internal tracking is acceptable (fixed asset software reports, Excel, or other reporting format).
Do not include consumable items, such as paper, pens, binders, etc.
Send reports to Preparedness@health.mo.gov

## Slide 8: Supporting Documents and Monitoring
Document Retention
Section 2.4 of PHEP contracts (Reporting and Recordkeeping)
Section 2.4 of CRI contracts (Other Reporting Requirements)
Monitoring
Annual risk assessments
Email notification
Request for selected invoice documentation
Monitoring meeting – conversation
LPHA Administrator, Planner, and Program Staff
LPHAs may include other staff if needed
Technical assistance, providing information and resources
Supporting documents must be available for monitoring and auditing purposes.
If requested as part of PHEP/CRI monitoring, documentation is due within 10 business days

## Slide 9: QUESTIONS?
Preparedness@health.mo.gov
Annette Lopes (573) 522-5008
Rikae Melzer (573) 751-6190
Health.Mo.Gov

## Slide 10: Closing Slide
PROMOTING HEALTH AND SAFETY