FROM WORK PLAN
TO IMPACT

Tools for implementing, monitoring, evaluating, and reporting the five-year contract

PARTICIPANT WORKBOOK

MCH Services Program | Five-Year Contract Kickoff | October 2026

# How to use this workbook

Bring this workbook and your approved work plan to staff meetings, partner meetings, quarterly reviews, and progress-report preparation.

Complete the worksheets during the kickoff session using one real activity from your plan.

Revisit the annual action plan whenever staffing, partners, timelines, or delivery methods change.

Use the evidence tracker throughout the year—not only when the progress report is due.

Document adaptations and barriers as they happen.

Keep the intended outcome visible when making implementation decisions.

## My long-term “why”

By September 2031, I hope the following will be different in my community, organization, or partnerships:

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# 1. Contract-to-impact cycle

Need and local context

Five-year work plan

Annual action plan

Implementation

Monitoring

Evaluation

Progress reporting

Improvement and sustainability

↓

↓

↓

↓

↓

↓

↓

## Reflection

Where does your team currently have the strongest system? Where is the greatest gap?

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# 2. Spectrum of Prevention quick reference

| Level | Primary change | Examples |
| --- | --- | --- |
| Strengthen individual knowledge and skills | Change in an individual’s knowledge, confidence, skill, or ability. | Education, coaching, skill practice, navigation. |
| Promote community education | Change in awareness, knowledge, or norms across a broader audience. | Campaigns, fairs, media, community presentations. |
| Educate providers | Change in the knowledge or practice of professionals and trusted helpers. | Provider training, toolkits, consultation, skill building. |
| Foster coalitions and networks | Change in coordination, shared action, relationships, or resource use. | Coalition work, shared plans, coordinated referral or messaging. |
| Change organizational practices | Change in routine systems, services, procedures, or workflows. | Screening workflow, documentation process, service integration. |
| Influence policy and legislation | Change in formal rules, policies, ordinances, or legislative conditions. | Policy development, adoption, implementation, advocacy where allowable. |

Ask: What is this activity primarily designed to change? Then check whether it clearly supports the shared outcome.

# 3. Logic model cheat sheet

| Component | Question | Contract examples |
| --- | --- | --- |
| Inputs | What we invest | Staff, funding, time, partners, materials, data |
| Activities | What we do | Train, educate, screen, convene, refer, develop policy |
| Outputs | What we directly produce | Sessions, people reached, referrals, products, policies drafted |
| Short-term outcomes | Immediate changes | Knowledge, awareness, confidence, skills, readiness |
| Intermediate outcomes | Changes in action or systems | Behavior, practice, workflow, service use, policy adoption/implementation |
| Long-term outcomes | Broader conditions | Health, quality of life, access, equity, morbidity or mortality indicators |

## My activity’s if–then story

### If we have…

________________________________________________________________________________

________________________________________________________________________________

### then we can…

________________________________________________________________________________

________________________________________________________________________________

### which will directly produce…

________________________________________________________________________________

________________________________________________________________________________

### so we expect the following short-term change…

________________________________________________________________________________

________________________________________________________________________________

### which should support the following intermediate or long-term change…

________________________________________________________________________________

________________________________________________________________________________

# 4. Output or outcome?

Outputs show effort and delivery. Outcomes show change.

| Example | Activity | Output | Outcome/change |
| --- | --- | --- | --- |
| Conduct two provider trainings | ☐ | ☐ | ☐ |
| Thirty-two providers attend | ☐ | ☐ | ☐ |
| Providers report increased referral confidence | ☐ | ☐ | ☐ |
| Develop a written screening policy | ☐ | ☐ | ☐ |
| The board adopts the policy | ☐ | ☐ | ☐ |
| Distribute 500 campaign cards | ☐ | ☐ | ☐ |
| More caregivers identify a trusted resource | ☐ | ☐ | ☐ |
| Convene a quarterly partner meeting | ☐ | ☐ | ☐ |

One output in my work plan that needs a corresponding outcome measure:

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# 5. Annual implementation planning worksheet

Selected Spectrum section: ________________________________________________

Five-year outcome: _________________________________________________________

Annual activity: ____________________________________________________________

## Intended change

What change should this activity support this year?

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## Key steps

What must happen before, during, and after the visible activity?

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## Responsible people

Who owns each step? Who is the backup?

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## Partners and stakeholders

Who must be consulted, involved, or informed?

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## Priority population and reach

Who should be reached? How will they be recruited or engaged?

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## Resources

What staff time, materials, space, funding, expertise, or technology are needed?

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## Timeline and milestones

What are the dates, dependencies, and review points?

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## Documentation and evidence

What will show implementation, reach, quality, and change?

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## Potential barriers

What could interfere? What is the backup plan?

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## Approval or technical assistance

What must be clarified with leadership, program staff, or the nurse consultant?

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# 6. Implementation readiness checklist

| Domain | Ready | Needs attention | Stop/clarify |
| --- | --- | --- | --- |
| Purpose and alignment The activity clearly supports the approved outcome and is placed under the appropriate Spectrum level. | ☐ | ☐ | ☐ |
| People A lead, backup, and implementation roles are identified. | ☐ | ☐ | ☐ |
| Training and fidelity Staff and partners understand the purpose, core content, roles, and documentation requirements. | ☐ | ☐ | ☐ |
| Priority population The intended audience and recruitment or engagement approach are clear. | ☐ | ☐ | ☐ |
| Partners Partner roles, communication, and deliverables are clear. | ☐ | ☐ | ☐ |
| Resources Time, funding, materials, space, and technology are available or secured. | ☐ | ☐ | ☐ |
| Timeline Major steps and decision points are scheduled. | ☐ | ☐ | ☐ |
| Evidence Process and outcome evidence match the work-plan measure. | ☐ | ☐ | ☐ |
| Data responsibility Someone is assigned to collect, store, summarize, and review the information. | ☐ | ☐ | ☐ |
| Contract requirements Allowability, accessibility, plain language, privacy, and required approvals have been considered. | ☐ | ☐ | ☐ |
| Risks Likely barriers and backup strategies are documented. | ☐ | ☐ | ☐ |
| Review rhythm The team has a monthly or quarterly process for reviewing progress. | ☐ | ☐ | ☐ |

The first readiness issue our team will address:

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# 7. Barrier and adaptation log

Document changes as they happen: what changed, why, who was involved, what core purpose was preserved, and what the result was.

| Date | Barrier or opportunity | Adaptation/response | Who approved or participated | Core element preserved | Result / follow-up |
| --- | --- | --- | --- | --- | --- |

Questions to ask before changing an activity:

What problem or barrier are we trying to solve?

What outcome must remain unchanged?

What part can change without weakening the pathway?

Who must be involved or approve the change?

How will we evaluate whether the adaptation improved implementation?

# 8. Evaluation planning worksheet

Activity: ____________________________________________________________________

Outcome and outcome measure: ___________________________________________________

| Type | Evaluation question | Indicator/evidence | Who collects it? | When reviewed? |
| --- | --- | --- | --- | --- |
| Process | Did we carry out the activity as planned? |  |  |  |
| Reach | Did we reach the intended population and partners? |  |  |  |
| Short-term change | Did knowledge, confidence, skill, awareness, or readiness change? |  |  |  |
| Intermediate change | Did behavior, practice, workflow, referral, service, or policy change? |  |  |  |
| Learning | What helped, what interfered, and what should change next time? |  |  |  |

Start with the question. Collect the least burdensome evidence that can credibly answer it.

## Data collection fit

Is the method appropriate for literacy, language, age, technology access, privacy, and accessibility needs?

Is the question neutral and understandable?

Will the information actually be used for reporting or a decision?

Is responsibility for data storage and review clear?

# 9. Progress-report evidence tracker

| Date/activity | What was done | Who/reach | Output evidence | Outcome evidence | Barrier/adaptation | Next step/TA need |
| --- | --- | --- | --- | --- | --- | --- |

Suggested review rhythm: brief monthly update and deeper quarterly review with staff or partners.

# 10. Progress-report narrative builder

## What was planned?

Name the outcome, measure, method, and annual activity.

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## What happened?

Describe the major implementation steps and how the activity was delivered.

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## How much and who?

Report outputs, reach, priority population, and partner involvement.

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## What changed?

Report the outcome evidence and explain what it means.

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## What affected the work?

Describe barriers, facilitators, adaptations, and unintended outcomes.

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## What comes next?

Identify improvements, follow-up, sustainability steps, and technical-assistance needs.

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## Quality check

Specific: Does the narrative identify who, what, when, and how much?

Evidence-based: Are claims supported by data or documentation?

Honest: Are limitations and barriers described without overstating results?

Improvement-oriented: Does the narrative explain what will happen next?

# 11. Sustainability planning

What should still exist, be routine, or be stronger by September 2031?

| Sustainability area | What we will begin building now |
| --- | --- |
| Policies/procedures |  |
| Trained staff and backup capacity |  |
| Partner ownership and coordination |  |
| Reusable tools, materials, or data systems |  |
| Leadership support and resources |  |
| Evidence and communication of value |  |

One Year 1 sustainability step:

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# 12. My 30-day contract action plan

START One activity or preparation step I will begin: ________________________________________________________________________ ________________________________________________________________________

PARTNER One person or organization I will involve: ________________________________________________________________________ ________________________________________________________________________

TRACK One piece of evidence I will collect: ________________________________________________________________________ ________________________________________________________________________

ANTICIPATE One barrier I will plan for: ________________________________________________________________________ ________________________________________________________________________

ASK One question or technical-assistance need I will raise: ________________________________________________________________________ ________________________________________________________________________

Name: ___________________________________________    Date: _______________________

Person I will share this commitment with: ________________________________________

# Selected references

Centers for Disease Control and Prevention. (2024). CDC Program Evaluation Framework, 2024. MMWR Recommendations and Reports, 73(6), 1–37.

Centers for Disease Control and Prevention. (2024). Developing and Using a Logic Model.

Cohen, L., & Swift, S. (1999). The spectrum of prevention: Developing a comprehensive approach to injury prevention. Injury Prevention, 5(3), 203–207.

Frieden, T. R. (2014). Six components necessary for effective public health program implementation. American Journal of Public Health, 104(1), 17–22.

Issel, L. M., & Wells, R. (2018). Health Program Planning and Evaluation: A Practical, Systematic Approach for Community Health (4th ed.).

McKenzie, J. F., Neiger, B. L., & Thackeray, R. (2017). Planning, Implementing, & Evaluating Health Promotion Programs: A Primer (7th ed.).

Prevention Institute. The Spectrum of Prevention.

W.K. Kellogg Foundation. Logic Model Development Guide.

CHES® examination study materials, Chapters 2–4.

- This workbook paraphrases and adapts program-planning, implementation, and evaluation concepts for practical application to the MCH Services Program contract.